## checklist
Hour Log Application Upgrade to Integrate ReA Procedure and Checklist
# | Date/Time | Description | Status | Performed By | Comments
28 |  | Start
27 | 2015-06-10 | Get approval from Operations Department Head (ODH) | Done | VV
26 | 2015-06-10 | Schedule upgrade in consultation with ODH | Done | VV
25 | 2015-06-10 | Submit Utility Notice (at least 2 days in advance) | Done | VV | Not 2 days in advnace but informed Morrissey. Found out on 6/12 that the Utility notice never went through (I can't add them so I request Kelly) but it is too late now.
24 | 2015-06-10 | Add upgrade to Short Term Schedule | Done | VV | Not necessary during shutdowns
23 | 2015-06-10 | Inform owners of dependent systems (DataU, Hallway Display etc) | Done | VV
22 | 2015-06-10 | Make sure that package for current version is available at /projects/hourlog/scm, in case we need to revert to current version | Done | VV
21 | 2015-06-10 | Copy package for new version at /project/hourlog/scm | Done | VV
20 | 2015-06-10 | Deploy Hour Log on Test Server | Done | VV
19 | 2015-06-11 | Perform Automated & Manual Tests | Done | VV
18 | 2015-06-12 | Get the test results approved by ODH | Done | VV
17 | 2015-06-12 | Undeploy current Hour Log from production server | Done | VV
16 | 2015-06-12 | Backup the Hour Log production database | Done | VV
15 | 2015-06-12 | Backup Hour Log database | Done | VV
14 | 2015-06-12 | Upgrade Hour Log Schema to v1.1 | Done | VV
13 | 2015-06-12 | Migrate data from current database to new schema | Done | VV
12 | 2015-05-28 | Upgrade Olog to new version | Done | EB
11 | 2015-05-28 | Migrate Olog to new server | Done | EB
10 | 2015-06-12 | Make Olog inaccessible to others | Done | VV
9 | 2015-06-12 | Backup Olog and Jackrabbit databases | Done | VV
8 | 2015-06-12 | Migrate Hour Log databaes to Olog | Done | VV
7 | 2015-06-12 | Migrate Hour Log attachments to Olog | Done | VV
6 | 2015-06-12 | Make Olog accessible to everyone | Done | VV
5 | 2015-06-12 | Deploy new version of Hour Log on production server | Done | VV
4 | 2015-06-12 | Run read-only tests | Done | VV
3 | 2015-06-12 | Test dependent systems: DataU, Hallway Display, A1900 web page, Intra Enterprise On Call page. | Done | VV
2 |  | If anything fails, revert to stable version of Hour Log
1 | 2015-06-12 | Otherwise, announce new release to stakeholders (ODH, API users, development team). Send Release Notes to stakeholders. | Done | VV
0 |  | End