## checklist
Hour Log Application Upgrade Procedure and Checklist
|  | Version | 1.2 | 2015-04-08
# | Date/Time | Description | Status | Performed By | Comments
19 |  | Start
18 | 2015-05-27 | Get approval from Operations Department Head (ODH) | Done | VV
17 | 2015-05-27 | Schedule upgrade in consultation with ODH | Done | VV
16 | 2015-05-27 | Submit Utility Notice (at least 2 days in advance) | Done | AS
15 | 2015-05-27 | Add upgrade to Short Term Schedule | Done | VV
14 | 2015-10-21 | Inform owners of dependent systems (DataU, Hallway Display etc) | Done | VV
13 | 2015-05-29 | Make sure that package for current version is available at /projects/hourlog/scm, in case we need to revert to current version | Done | VV
12 | 2015-05-29 | Copy package for new version at /project/hourlog/scm | Done | AP, VV | Adam finished most of the tests by 5/23/2015. Rest done by Vasu
11 | 2015-05-29 | Deploy Hour Log on Test Server | Done | VV
10 | 2015-05-29 | Perform Automated & Manual Tests | Done | VV
9 | 2015-05-29 | Get the test results approved by ODH | Done | VV
8 | 2015-05-29 | Undeploy current Hour Log from production server | Done | VV | started at about 13:15
7 | 2015-05-29 | Backup the Hour Log production database | Done | VV
6 | 2015-05-29 | Migrate to v1.3 of schema | Done | VV | done at 13:24
5 | 2015-05-29 | Deploy new version of Hour Log on production server | Done | VV | done at 13:26
4 | 2015-05-29 | Run read-only tests | Done | VV | GF hung. Had to restart GF. done at 13:54
3 | 2015-05-29 | Test dependent systems: DataU, Hallway Display, A1900 web page, Intra Enterprise On Call page. | Done | VV
2 | 2015-05-29 | If anything fails, revert to stable version of Hour Log | Done | VV | Everything looks fine
1 | 2015-05-29 | Otherwise, announce new release to stakeholders (ODH, API users, development team). Send Release Notes to stakeholders. | Done | VV
0 |  | End |  |  | Done by about 14:00