## Terms
EVM Analysis Terms
# | Term | Abbrev. | Description | Formula/Value
1 | Budget at Completion | BAC | Baseline project cost
2 | Actual Cost | AC | Total costs incurred in completing work during a given period
3 | Earned Value | EV | Physical work completed during a given period
4 | Planned Value | PV | Physical work scheduled for completion during a given period
5 | Cost Variance | CV | Cost overrun during a given period | EV-AC
6 | Cost Performance Index | CPI | Cost efficiency ratio | EV/AC
7 | Schedule Variance | SV | Schedule slipped during a given period | EV-PV
8 | Schedule Performance Index | SPI | Schedule efficiency ratio | EV/PV
9 | Estimate to Completion | ETC | Expected additional cost needed | EAC-AC
10 | Estimate at Completion | EAC | Expected total cost | BAC/CPI
11 | Variance at Completion | VAC | Estimated cost overrun at end of project | BAC-EAC
12 | To-Complete Performance Index | TCPI | Ratio of remaining work and remaining resources
| TCPI Cost | TCPI-C | Ratio of remaining work and remaining funds | BAC-EV)/(BAC-AC)
| TCPI Schedule* | TCPI-S | Ratio of remaing work and remaining time | (BAC-EV)/(BAC-PV)
13 | Average Index |  | Average of CPI and SPI | (CPI+SPI)/2
14 | Status Field |  | Color Codes:
|  |  | GREEN = On track | ³1.0
|  |  | YELLOW = Slightly behind schedule/budget | ³0.85 but <1.0
|  |  | RED = Needs immediate attention | ³0.65 but <0.85
|  |  | BLACK = Needs to be killed or restored | <0.65
*Note: TCPI-S is not a standard and is not defined in literature.

## Data
Project EVM Report
| Project ID |  | Project Description | [9 empty] | Work Order #
| HourLog |  | New Hour Log | [9 empty] | RC100609.14100.W02655
| Budget |  | Earned | Actual | Cost Variance |  | Schedule Variance |  | Index |  | Forecast |  |  |  | TCPI |  |  |  | Schedule Forecast
Status Date | BAC | PV | EV | AC | $ | % | $ | % | CPI | SPI | ETC | EAC | VAC (%) | VAC ($) | Cost | Sched | Average Index | Status | DAS | DAC | BAC-T | EAC-T | ETC-T | VAC-T
2014-10-06 | 97500 | 31560 | 3200 | 2800 | 400 | 1.267% | -28360 | -89.86% | 1.1429 | 0.10139 | 82512.5 | 85312.5 | 12.5% | 12187.5 | 0.99578 | 1.4301 | 0.62213 | Black | 2014-09-01 | 2015-02-09 | 161 | 2019-01-05 20:42 | 1552.8625 | -1426.8625 | -886.3%
2014-10-10 | 97500 | 38520 | 16460 | 6400 | 10060 | 26.12% | -22060 | -57.27% | 2.5719 | 0.42731 | 31510.0851 | 37910.0851 | 61.12% | 59589.9149 | 0.88957 | 1.374 | 1.4996 | Green | 2014-09-01 | 2015-02-09 | 161 | 2015-09-12 18:36 | 337.7752 | -215.7752 | -134%
2014-10-24 | 97500 | 48840 | 20140 | 13000 | 7140 | 14.62% | -28700 | -58.76% | 1.5492 | 0.41237 | 49934.4588 | 62934.4588 | 35.45% | 34565.5412 | 0.9155 | 1.5898 | 0.9808 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-09-26 10:18 | 337.429 | -229.429 | -142.5%
2014-10-31 | 97500 | 53440 | 23400 | 16400 | 7000 | 13.1% | -30040 | -56.21% | 1.4268 | 0.43787 | 51933.3333 | 68333.3333 | 29.91% | 29166.6667 | 0.91369 | 1.6818 | 0.93235 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-09-03 16:27 | 307.6855 | -206.6855 | -128.4%
2014-11-07 | 97500 | 58040 | 25576 | 16850 | 8726 | 15.03% | -32464 | -55.93% | 1.5179 | 0.44066 | 47385.025 | 64235.025 | 34.12% | 33264.975 | 0.8918 | 1.8227 | 0.97926 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-09-01 08:38 | 298.3597 | -204.3597 | -126.9%
2014-11-14 | 97500 | 63560 | 32420 | 23500 | 8920 | 14.03% | -31140 | -48.99% | 1.3796 | 0.51007 | 47173.9667 | 70673.9667 | 27.51% | 26826.0333 | 0.87946 | 1.9175 | 0.94482 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-07-13 15:27 | 241.6434 | -154.6434 | -96.05%
2014-11-24 | 97500 | 68160 | 39260 | 28500 | 10760 | 15.79% | -28900 | -42.4% | 1.3775 | 0.576 | 42278.1457 | 70778.1457 | 27.41% | 26721.8543 | 0.84406 | 1.985 | 0.97677 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-06-07 12:22 | 195.515 | -118.515 | -73.61%
2014-12-01 | 97500 | 70920 | 43200 | 31600 | 11600 | 16.36% | -27720 | -39.09% | 1.3671 | 0.60914 | 39719.4444 | 71319.4444 | 26.85% | 26180.5556 | 0.82398 | 2.0429 | 0.98811 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-05-23 07:24 | 173.3083 | -103.3083 | -64.17%
2014-12-08 | 97500 | 75520 | 47220 | 37600 | 9620 | 12.74% | -28300 | -37.47% | 1.2559 | 0.62526 | 40036.5947 | 77636.5947 | 20.37% | 19863.4053 | 0.8394 | 2.2875 | 0.94056 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-05-16 11:47 | 159.4909 | -96.4909 | -59.93%
2014-12-15 | 97500 | 80186.67 | 50790 | 41900 | 8890 | 11.09% | -29396.67 | -36.66% | 1.2122 | 0.6334 | 38534.1406 | 80434.1406 | 17.5% | 17065.8594 | 0.84011 | 2.6979 | 0.92278 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-05-13 04:26 | 149.185 | -93.185 | -57.88%
2014-12-22 | 97500 | 83386.67 | 55190 | 51100 | 4090 | 4.905% | -28196.67 | -33.81% | 1.08 | 0.66186 | 39174.5063 | 90274.5063 | 7.411% | 7225.4937 | 0.91185 | 2.9979 | 0.87095 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-05-02 06:07 | 131.2552 | -82.2552 | -51.09%
2014-12-29 | 97500 | 84946.67 | 59610 | 58000 | 1610 | 1.895% | -25336.67 | -29.83% | 1.0278 | 0.70173 | 36866.6331 | 94866.6331 | 2.701% | 2633.3669 | 0.95924 | 3.0183 | 0.86475 | Yellow | 2014-09-01 | 2015-02-09 | 161 | 2015-04-18 10:21 | 110.4315 | -68.4315 | -42.5%
Formulas:
EAC-T = [Schedule Forecast] +([DAC]-[Schedule Forecast])/[SPI]
Note on V8: How Long will take to complete the project? These are NOT found in EVM literature
Note on T9: Green: On Track Yellow: Slightly Slipping Red: Needs Attention Black: Terminate or restore