## Slide 1: New Hour Log: Project Plan Baseline
Vasu Vuppala
26 August 2014

## Slide 2: Overview
Scope
Strategy
Schedule
Resources
Risks
Conclusion

## Slide 3: Project Scope
Develop a new implementation of Hour Log that has
  All the functionality of Current Hour Log (CHL)
  Ability to manage multiple Facilities
Migrate data from CHL to New Hour Log (NHL)
Interface with external systems through APIs
  Approved Experiments, Trouble Reports, Training System, Logbook Service etc.
Upgrade systems that depend on Hour Log:
  Data U Display
Develop API to interface with Hour Log programmatically
Train users on NHL
Switch over from NHL to CHL

## Slide 4: Out of Scope
Upgrade of Hallway Display:
  NHL will provide access to such data through an API.
  However, upgrading of Hallway Display itself is not within the scope of this project
Upgrade of any system that is dependent on Hour Log except Data U Display

## Slide 5: Hallway Display
Upgrading of Hallway Display is not in the scope of this project
Business Application IT Department (BIT) will upgrade Hallway Display
BIT will provide requirements for desired interface to Hour Log

## Slide 6: WBS
ID | Name | Description | Owner
HL | New Hour Log | Entire project | CCD
HL-FF | Develop Functional Features | GUI, Reports, Interface with external systems | CCD
HL-API | Develop API | API to access Hour Log data | CCD
HL-DS | Upgrade Dependent Systems | Data U Display | CCD
HL-QA | Quality Assurance | Test plans, automated tests, ACL | CCD
HL-DOC | Documentation | SRS, design, user, API, installation manuals | CCD
HL-TRN | Train users | Training of operators | CCD
HL-SO | Switch-over | Data migration, switch to new Hour Log | CCD
HL-PM | Project Management | Project management activities | CCD

## Slide 7: Project Strategy
Develop a beta version with most of the functionality but with limited interfaces to external systems
Get feedback
Automate Data Migration
Dependent Systems:
  Identify systems that are dependent on Hour Log.
  Find stakeholders, for upgrading them
  Develop NHL APIs for them
External systems:
  Identify external systems that Hour Log depends on
  Interface with them through APIs instead of directly accessing the databases
Quality Assurance
  Develop test plans
  Develop automated and manual tests
Switch over to NHL

## Slide 8: Schedule
MS Project Schedule (if any one is interested)
Takes NSCL Holidays into account
But does not take into account vacation and travel
  EPICS Meeting in October (Eric may be gone for a week)

## Slide 9: Milestones
# | Name | Description | Owner | Expected Completion
1 | Hour Log Release | Periodic Releases (Sep, Oct, Nov, Dec 2014, and Jan 2015) | CCD | Every Month. Final one on 1/5/15
2 | Data U Display | Upgrade of Data U | CCD | 3rd Week of November
3 | API for Hallway Display | Requirements to be provided by BIT. | CCD | 3rd Week of September
4 | APIs for Trouble Reports and Training Systems | See requirements for the interfaces | BIT | 1st Week of October
5 | User Training |  | CCD | 1st Week of December
6 | UAT | User Acceptance Test | Operations | 2nd Week of December
7 | Switch over |  | CCD | January 2015 Shutdown
8 | Project Completion |  | CCD | February 2015

## Slide 10: Risks
# | Risk | Root Cause | Probability | Impact | Response
1 | Unknown Systems Dependent on Hour Log | Known Unknowns. | Medium | High | 1. Announce Hour Log changes to the entire lab in September or October.
2 | Systems Hour Log Depends on: TR, Training, Olog, Experiments | Interfaces not ready | Medium | High | 1. Weekly progress report (EVM) 2. Stakeholder escalation
*NHL Beta Can Replace Current Hour Log

## Slide 11: Budget
# | Work Package | Effort (Person Hours)
1 | Features (GUI, Reports etc) | 250
2 | Interfacing with External Systems (Olog, Tr, Training) | 300
3 | Data U | 60
4 | Application Programming Interface | 30
5 | QA | 100
6 | Documentation | 80
7 | Project Management | 60
 | Total Planned | 900
 | Total Performed | 450
No Material Procurements

## Slide 12: Conclusion
Switch over to NHL during January Shutdown
Dependent on other systems: Olog, TR, Training, Data U
Hallway Display should be ready by then
Details in Project Plan
  Business Need
  Communications Plan: Project Performance
  Quality Management Plan
  Configuration Management Plan
  Project Organization
  Change Control
Next Steps:
  Baseline Project Plan
  DCC Project Plan