## Final
Effort Estimation |  | Date: 18-Feb-2015
Project: NHL |  | Phase:
Units: Person Hours |  | By:
WBS ID | Task Name | Estimates |  |  | Contingency | Total
|  | O | R | P
| Changes to Olog API: for importing of existing log entries, including attachments, creation of entries from a service, backdating, heartbeat | 80 | 120 | 160 |  | 120
| Setting up new Olog: | 8 | 8 | 8 |  | 8
| Migrating data from old Olog to new Olog | 8 | 8 | 8 |  | 8
| Olog Documentation | 24 | 32 | 40 |  | 32
| Scripts to import Hour Log notes to Olog. | 60 | 80 | 100 |  | 80
| Integration with Hour Log | 20 | 40 | 80 |  | 43.3333
| Olog Integration Testing | 40 | 40 | 60 |  | 43.3333
0
| Hour Log Remaining Documentation (Requirements, Design, Installation, User, Systems manuals) | 40 | 60 | 80 |  | 60
| Test Automation | 80 | 120 | 160 |  | 120
| Current Bug Fixes | 20 | 40 | 80 |  | 43.3333
| User Database Interface | 40 | 40 | 60 |  | 43.3333
| Reports (fixes and new ones) | 80 | 80 | 120 |  | 86.6667
| Code Improvements | 40 | 40 | 40 |  | 40
| Additional APIs | 20 | 40 | 80 |  | 43.3333
| Monitoring Instrumentation | 40 | 40 | 80 |  | 46.6667
| API key management and authorization | 24 | 40 | 48 |  | 38.6667
| Application Properties in Database | 24 | 24 | 40 |  | 26.6667
0
0
0
0
0
0
0
0
0
0
0
| Total |  |  |  |  | 883.3333
| Contingency |  |  |  |  | 88.3333
| Total Estimate |  |  |  |  | 971.6667
Note on D6: In Person Hours
Note on D7: Optimistic
Note on E7: Realistic
Note on F7: Pessimistic