## checklist
Switch-Over to New Hour Log (NHL) - Checklist
|  | Version | 0.8 | Date | 2015-03-02
2015-03-02
# | Date/Time | Description | Status | Owner | Performed By | Comments
1 | 10:20 | Deploy New Hour Log v1.x on Production Server | ok | Controls | VV
2 | 10:50 | Migrate Data to Production | ok | Controls | VV
3 | 11:05 | Copy attachments under /srv/hourlog/blobstore | ok | Computer Dept | AP, TR | Copying under /projects, makes the file empty after sometime
4 | 2015-01-01 | Make production Hour Log accessible from outside the lab |  | Computer Dept | VV
5 | 11:10 | Perform Automated & Manual Tests | NOK | Controls | VV | APIs not working. Recompiled and redeployed. Few other issues. See test summary
6 | 11 | Test New Data U Display | OK | Controls | VV
7 |  | Test New Hallway Display | OK | Biz IT (initiated by Controls) | JA
8 | 2014-12-01 | Announce Switch-Over a week in advance | OK | Operations | AS
9 | 9:00 | Create Utility Notices | NOK | Controls/Operations | VV | Got delayed. Notices should be given 2 days in advance
10 | 14:10 | Put Current Hour Log in Read-Only Mode | NOK | Computer Dept | AP, TR, VV | Database writable even after revoking privileges
11 | 17:20 | Backup the Hour Log databases | ok | Controls/Computer Dept | AP, VV
12 | 17:30 | Migrate Data to Production | ok | Controls | VV
| 17:40 | Copy attachments under /srv/hourlog/blobstore | ok | Computer Dept | AP, TR
14 | 18:30 | Perform Automated & Manual Tests (Limited) | NOK | Controls | VV | Migrated attachments are corrupted. Disk space issue.
15 | 23:40 | Test New Data U Display | OK | Controls | VV
16 |  | Test New Hallway Display |  | Biz IT (initiated by Controls) | JA
17 |  | If anything fails, switch back to Current Hour Log |  | Controls
2015-03-03
18 | 9:00 | Switch Data U Display to new version | OK | Computer Dept/Controls | AS
19 | 9:00 | Change links on Intra Enterprise to new Hour Log | OK | Biz IT (initiated by Controls) | JA
20 | 9:00 | Switch Hallway Display to new version | OK | Biz IT (initiated by Controls) | JA
21 | 17:14 | Announce Switch Over of New Hour Log | OK | Operations | AS
22 | 17:14 | Announce Switch Over of new Data U Display | OK | Operations | AS