Hour Log – Change Request

N20000-PL-000209-R001

Issued 11 February 2015

Prepared by Approved by



Approved by



# Table of Contents

[Table of Contents 1](#_Toc411425680)

[Revision History 1](#_Toc411425681)

[Authorizing Document 1](#_Toc411425682)

[Authorized Documents 1](#_Toc411425683)

[Authorized Committees and Boards 1](#_Toc411425684)

# Revision History

|  |  |  |
| --- | --- | --- |
| Revision | Issued | Changes |
|  | 11 February 2015 | Initial document |

# Authorizing Document

None.

# Authorized Documents

None.

# Authorized Committees and Boards

None.

|  |  |
| --- | --- |
| **Change Request Form** | |
| *Project*: Hour Log | *Change #*: 01 |
| *Requestor*: Vasu Vuppala | *Submitted on*: 11-Feb-2015 |
| *Change Type*: Scope and Schedule Change | *Response due by*: |
| *Description*:   1. Switchover Milestone was missed during the January Shutdown. The switchover will be performed during first week of March 2015. 2. Interfaces to Olog Logbook Service could not be completed. They will be completed in the next version of NHL. | |
| *Impact Analysis*:   1. Switchover will be delayed till March 2015. 2. Hour Log will be implemented for ReA Facility once new Olog Interface is ready. 3. The project will need additional 628 hours. 4. New project plan (and schedule) must be submitted to DCC. | |
| *Final Recommendation*:  Approved | |
|  | |